## RMS
Screen/Function | Feature | Sub Feature | Guest | Member | Admin | Project Manager | PMO Manager | QA Manager | Dept Manager | Planned-In | In Charge | Done-In | RDS | Status | Notes | Updated | Update Details
User Login | Common |  | x | x | x |  |  |  |  | Iteration 1 | NghiaNM | Iteration 2 | II.1.1 | Done |  | Not Yet
User Register | Common |  | x | [6 empty] | Iteration 1 | NghiaNM | Iteration 1 | II 1.2 | Done |  | Iteration 3 | Add Verify email
Password Reset | Common |  |  | x | x |  |  |  |  | Iteration 1 | NghiaNM | Iteration 1 | II 1.3 | Done |  | Not Yet
Dashboard | Common |  |  | x | x |  |  |  |  | Iteration 1 | DatND | Iteration 1 | II.1.4 | Done |  | Iteration 3 | - Completed navbar and header. - Update UI with chart, and statistics.
Setting List | Adminstration |  |  |  | x |  |  |  |  | Iteration 1 | AnhNQ | Iteration 1 | II.2.1 | Done |  | Not Yet
Setting Details | Adminstration |  |  |  | x |  |  |  |  | Iteration 1 | AnhNQ | Iteration 1 | II.2.2 | Done |  | Not Yet
User List | Adminstration |  |  |  | x |  |  |  |  | Iteration 1 | MinhPN | Iteration 1 | II.2.3 | Done |  | Not Yet
User Details | Adminstration |  |  |  | x |  |  |  |  | Iteration 1 | MinhPN | Iteration 1 | II.2.3 | Done |  | Not Yet
User Profile | User Feature |  |  | x | x |  |  |  |  | Iteration 1 | DatND | Iteration 1 | II.1.5 | Done |  | Iteration 3 | - Add email verification when changing emails. - Show validate errors message under inputs. - Go to the setting page at first. - Chang image name. - Validat input in service layer.
Password Change | User Feature |  |  | x | x |  |  |  |  | Iteration 1 | DatND | Iteration 1 | II.1.5 | Done |  | Iteration 3 | - Logout and redirect to login when change successful.
Group List | Adminstration |  |  |  | x |  |  |  |  | Iteration 1 | TruongVV | Iteration 1 | II.2.4 | Done |  | Not Yet
Group Details | Adminstration |  |  |  | x |  |  |  |  | Iteration 1 | TruongVV | Iteration 1 | II.2.4 | Done |  | Not Yet
User Authorization | System Function |  | x | x | x |  |  |  |  | Iteration 1 | DatND | Iteration 3 |  | Done |  | Not Yet
Domain Users | Domain Manament | [8 empty] | Iteration 2 | MinhPN | Iteration 2 | II.4.1 | Done |  | Not Yet
Domain Settings | Domain Manament | [8 empty] | Iteration 2 | MinhPN | Iteration 2 | II.4.2 | Done |  | Not Yet
Phase List | Domain Manament | [8 empty] | Iteration 2 | NghiaNM | Iteration 2 | II.4.1 | Done |  | Iteration 3 | - Fix UI - List project phase - Filter - Add new
Phase Details | Domain Manament | [8 empty] | Iteration 2 | NghiaNM | Iteration 2 | II4.1 | Done |  | Iteration 3 | Update Details
Domain Criteria | Domain Manament | [8 empty] | Iteration 2 | MinhPN | Iteration 2 | II.4.3 | Done |  | Not Yet
Criteria Details | Domain Manament | [8 empty] | Iteration 2 | NghiaNM | Iteration 3 | II4.2 | Done |  | Not Yet
Project List | Project Magement |  |  | x | x | x |  |  | x | Iteration 2 | TruongVV | Iteration 2 | II.3.5 | Done |  | Not Yet
Project Details | Project Magement |  |  | x | x | x |  |  | x | Iteration 2 | TruongVV | Iteration 2 | II.3.6 | Done |  | Not Yet
Milestone List | Project Magement |  |  | x | x | x | x | x | x | Iteration 2 | AnhNQ | Iteration 2 | II.3.2 | Done |  | Iteration 3 | Add Sort into all field of table
Milestone Details | Project Magement |  |  | x |  | x |  |  |  | Iteration 2 | AnhNQ | Iteration 2 | II.3.2 | Done |  | Iteration 3
Project Criteria | Project Magement |  |  | x | x | x | x | x | x | Iteration 2 | DatND | Iteration 2 | II.3.1 | Done |  | Iteration 3
Project Members | Project Magement |  |  | x | x | x | x | x | x | Iteration 2 | DatND | Iteration 2 | II.3.3 | Done |  | Iteration 3 | - Fixed UI, remove status collum. - Add quick search for project config
Team List | Project Magement |  |  | x | x | x | x | x | x | Iteration 2 | DatND | Iteration 2 | II.3.4 | Done |  | Iteration 3 | - Filtered by milestone at start. - Fixed team structure logic.
Team Details | Project Magement |  |  |  | x | x | x | x | x | Iteration 2 | DatND | Iteration 2 | II.3.4 | Done |  | Iteration 3 | - Filtered add member list to team by milestone.
Allocation List | Allocation Magement |  |  | x | x | x | x | x | x | Iteration 3 | DatND | Iteration 3 |  | Done |  | Not Yet
Allocation Details | Allocation Magement |  |  |  | x | x | x | x | x | Iteration 3 | DatND | Iteration 3 |  | Done |  | Not Yet
Exception Handling | System Function | [8 empty] | Iteration 3 | DatND | Iteration 3 |  | Done |  | Not Yet
Scope List | Project Magement | [8 empty] | Iteration 3 | MinhPN | Iteration 3 |  | Done |  | Not Yet
Scope Details | Project Magement | [8 empty] | Iteration 3 | MinhPN | Iteration 3 |  | Done |  | Not Yet
Project Issues | Project Magement |  |  | x | x | x | x | x | x | Iteration 3 | AnhNQ | Iteration 3 |  | Done |  | Not Yet
New Issue | Project Magement |  |  |  |  | x |  | x |  | Iteration 3 | AnhNQ | Iteration 3 |  | Done |  | Not Yet
Issue Details | Project Magement |  |  | x |  | x |  | x |  | Iteration 3 | AnhNQ | Iteration 3 |  | Done |  | Not Yet
Timesheet List | Project Magement | [8 empty] | Iteration 3 | TruongVV | Iteration 3 |  | Done |  | Iteration 3 | update group list can change status on list page, validate,fix change status to radio button... done.
Timesheet Details | Project Magement | [8 empty] | Iteration 3 | TruongVV | Iteration 3 |  | Done |  | Iteration 3 | update project list can filter by domain and department add button navigation to millestone , member can only view detail and have no permission to update detail,admin ,project QA,project management has right to change status....done.
Project Defect | Project Magement | [8 empty] | Iteration 3 | NghiaNM | Iteration 3 |  | Done |  | Iteration 3 | Update user list,setting list,eval list by domainId.
New Defect | Project Magement | [8 empty] | Iteration 3 | NghiaNM | Iteration 3 |  | Done |  | Not Yet
Defect Detail | Project Magement | [8 empty] | Iteration 3 | NghiaNM | Iteration 3 |  | Done |  | Not Yet
f
Note on D1: kiennt: Thay bằng tên user role thực tế để theo dõi quyền truy cập vào chức năng/màn hình
Note on K1: kiennt: Kế hoạch sẽ làm trong iteration nào?
Note on M1: kiennt: Thực tế đã làm xong trong iteration nào?
Note on N1: KienNT: Phân tích yêu cầu và thiết kế cho màn hình/chức năng được mô tả trong phần nào của tài liệu RDS?
Note on Q1: kiennt: Chức năng đã được update/bổ sung trong iteration nào sau khi được review
Note on R1: kiennt: Các nội dung update cụ thể, mô tả theo định dạng sau: dd/MMM-AccountName: Abc Xyz - dd/MMM: ngày thực hiện update (ví dụ 13/Oct) - AccountName: tài khoản của SV đã thực hiện update (ví dụ KienNT hoặc KienNTHe171209) - Abc Xyz: mô tả nội dung update